Event Planning Checklist

Event Name:	Date:

Once Date is Set

Determine Time

Determine event concept, theme, etc.

Establish budget

Send a save the date announcement

Outline logistics: rentals, furniture, parking security,

housekeeping

Put on VIP calendars: University, Involvement Center, office calendar

Prepare Baseline project

Meet with necessary VIPs

Other:

2 or More Months Out:

Set menu, decorations, musicians and AV needs – book all vendors and services

Performer needs: microphone, podium, stage, props

Design invitations or announcement

Invitation list

Ticket sales process or RSVP database

Directional signage

Draft a production schedule

Write scripts; include introductions of VIPs

Establish a publicity game plan

Decorations/theme development

Entertainment

Rain plan

Sponsorship

Ticketing/registration

Track expenses and update budget

Other:

Four Weeks Out:

Photographer

Mail invitations

Track ticket sales/RSVPs

Walk through every step of the event including the venue

Three Weeks Out:

Schedule briefings with VIPs

Call all vendors to confirm

Solicit volunteers

Walk through every step of the event

Other:

One Week Out:

Finalize production schedule. Include all telephone numbers.

Finalize scripts

Create and distribute staff/volunteer assignments

Walk through every step of the event

Three Days Out:

Give caterer final guarantee. Confirm delivery and set-up times.

Nametags and registration/check-in materials

Head table/seat assignments

Walk through every step of the event

Day Before:

Prepare an event bin: nametags in alpha order, office supplies, blank nametags, production schedule, scripts, guest list, giveaways, and signage.

Reconfirm: venue, catering, valet, musicians, florist, AV, etc.

Walk through every step of the event

Day of Event:

Check venue: temperature, cleanliness, furniture

arrangement, signage, restrooms, mic check

Confirm arrival of flowers, musicians, photographer, DJ

As unconfirmed guests arrive, make them a nametag and write their names on something to keep track.

Check names of VIPs for script/introductions

Get feedback

Day After Event:

Review attendance

Send appropriate thank-yous; include photos

Final budget review

Update the checklist

Determine how to “extend” event to those who could not attend

Update websites

Other details: