## Sheet1
Item | Description | Called | Scheduled | Projected Days | Actual Days | Days Needed to Complete According to Bid
1 | Get Permits | 2011-06-01 | 2011-06-03
2 | Plot Plan & Stake-Out | 2011-06-04 | 2011-06-05 | 2 | 2 | 2 | Release for Start Permits
3 | Order Temporary Power | 2011-06-01 | 2011-06-07
4 | Order Trusses, metal, wood beams | 2011-06-01 | 2011-06-15 |  |  | 1 | Connect Temporary Power
5 | Order windows | 2011-06-01 | 2011-06-20
6 | Order Exterior Doors | 2011-06-02 | 2011-06-22 |  |  | 2 | Stake Out
7 | Excavation | 2011-06-01 | 2011-06-07
8 | Footings | 2011-06-07 | 2011-06-15 |  |  | 5 | Excavation
9 | Inspection: Footings / Steel | 2011-06-15 | 2011-06-17
10 | Foundation | 2011-06-07 | 2011-06-20 |  |  | 3 | Footings
11 | Inspection: Foundation / Steel | 2011-06-15 | 2011-06-21
12 | Waterproof Foundation | 2011-06-20 | 2011-06-25 |  |  | 4 | Foundation
13 | Flatwork: Basement & Garage | 2011-06-17 | 2011-06-28
14 | Flatwork: Outside | 2011-06-17 | 2011-06-30 |  |  | 2 | Waterproofing
15 | Backfill & Rough Grade | 2011-06-20 | 2011-07-01
16 | Lumber | 2011-06-20 | 2011-07-02 |  |  | 1 | Backfill
17 | Framing | 2011-06-20 | 2011-07-02
18 | Plumbing Rough | 2011-07-02 | 2011-07-20 |  |  |  | Lumber Delivery
19 | HVAC Rough | 2011-07-02 | 2011-07-21
20 | Electric Rough | 2011-07-02 | 2011-07-23 |  |  | 7 | Start Framing
21 | Order Interior & Exterior Handrails | 7/2/ | 2011-07-23
22 | Fireplace box Installation | 2011-07-02 | 2011-07-23 |  |  | 10 | Finish Framing
23 | Tub & Shower Installation | 2011-06-20 | 2011-07-15
24 | Truss Delivery | 2011-07-02 | 2011-07-15 |  |  | 3 | Roofing
25 | Roof Load Materials | 2011-07-02 | 2011-07-15
26 | Masonry/Dry-in Installation | 2011-07-05 | 2011-07-25 |  |  | 6 | Rough Plumbing, Electric, HVAC
27 | Window Installation | 2011-07-20 | 2011-07-30
28 | Siding Installation | 2011-07-20 | 2011-07-30 |  |  | 2 | Insulation
29 | Gutter & Soffit Installation | 2011-07-30 | 2011-08-05
30 | Insulation | 2011-07-25 | 2011-08-03 |  |  | 5 | Drywall Hang
31 | Drywall Stock | 2011-07-30 | 2011-08-07
32 | Inspect: Framing/Plumbing Rough/Elec Rough | 2011-07-30 | 2011-08-02 |  |  | 9 | Drywall Tape/Sand
33 | Garage Door Installation | 2011-08-01 | 2011-08-08
34 | Drywall Hanging | 2011-07-25 | 2011-08-09 |  |  | 5 | Paint
35 | Inspect: Drywall | 2011-08-13 | 2011-08-15
36 | Drywall Taping | 2011-08-13 | 2011-08-16 |  |  | 3 | Hang Doors
37 | Order Showerdoors and Mirrors | 2011-08-13 | 2011-09-10
38 | Order Countertops | 2011-08-13 | 2011-09-10 |  |  | 5 | Tile
39 | Order Cabinets | 2011-08-13 | 2011-09-10
40 | Interior Paint | 2011-08-13 | 2011-09-01 |  |  | 2 | Carpet
41 | HVAC Final | 2011-09-10 | 2011-09-15
42 | Hang Interior Doors | 2011-09-10 | 2011-09-16 |  |  | 15 | Cabinets/ Final Trim
43 | Shelving Installation | 2011-09-16 | 2011-09-18
44 | Tile Installation | 2011-09-17 | 2011-09-25 |  |  | 3 | Final Plumbing/Electrical
45 | Countertop Installation | 2011-09-24 | 2011-09-30
46 | Plumbing Final/Install fixtures | 2011-09-30 | 2011-10-02 |  |  | 2 | Carpenter Final
47 | Electric Final / Install fixtures | 2011-10-02 | 2011-10-05
48 | Install Electric Meter and perm power | 2011-10-05 | 2011-10-10 |  |  | 1 | Drywall Touchup
49 | Interior & Exterior hand rails | 2011-10-05 | 2011-10-12
50 | Interior trim and Rehang doors | 2011-10-10 | 2011-10-15 |  |  | 1 | Paint Touchup
51 | Shower and Mirror Installation | 2011-10-15 | 2011-10-17
52 | Carpet Installation | 2011-10-12 | 2011-10-20 |  |  | 1 | Windows
53 | Paint Touch Up | 2011-10-15 | 2011-10-22
54 | Trim Carpenter | 2011-10-20 | 2011-10-25 |  |  | 1 | Final Inspection
55 | Construction clean | 2011-10-25 | 2011-10-28
56 | Occupancy Inspection | 2011-10-28 | 2011-11-01 |  |  | 1 | Walk Through