# Construction Schedule Template

Table 2.12.2-1

Proposed Project Construction Schedule Template

|  |  |  |  | Approx. |
| --- | --- | --- | --- | --- |
|  | TASK / MILESTONE | START | FINISH | On-Site |
|  |  |  |  | Manpower |
|  |  |  |  | for Task |
| 1 | Obtain EFSEC Site Certification | TARGET | 10/1/03 |  |
| 2 | Engineering/Design/Specifications/Surveys | 8/6/03 | 9/30/03 | 18 |
| 3 | Order/Fabricate Wind Turbines | 10/1/03 | 3/16/04 | 0 |
| 4 | Order/Fabricate Substation Transformer | 10/1/03 | 6/1/04 | 0 |
| 5 | Road Construction | 10/1/03 | 1/20/04 | 30 |
| 6 | Foundations Construction | 10/22/03 | 4/6/04 | 60 |
| 7 | Electrical Collection System Construction | 11/19/03 | 5/4/04 | 40 |
| 8 | Substation Construction | 1/14/04 | 6/1/04 | 20 |
| 9 | Wind Turbine Assembly and Erection | 3/17/04 | 9/21/04 | 40 |
| 10 | Plant Energization and Commissioning | 5/12/04 | 9/28/04 | 30 |
| 11 | Plant Substantial Completion | TARGET | 9/28/04 | 0 |
| 12 | Construction Punchlist Clean-Up | 8/25/04 | 11/16/04 | 15 |
|  |  |  | TOTAL | 253 |

Table 2.12.3-1

Construction Labor Force Mix (Approximate # Personnel)

| Construction Phase | Project | Field | Skilled Labor | Unskilled |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Management | Technical | & Equip | Labor |  |  |
|  | &Engineers | Staff | Operators |  | TOTAL |  |
| Engineering/Surveying/Design | 6 | 12 | 0 | 0 | 18 |  |
| Road Construction | 5 | 5 | 15 | 5 | 30 |  |
| Foundations Construction | 3 | 4 | 23 | 30 | 60 |  |
| Electrical Collection System | 2 | 3 | 23 | 12 | 40 |  |
| Construction |  |  |  |  |  |  |
| Substation Construction | 5 | 3 | 8 | 4 | 20 |  |
| Wind Turbine Assembly and | 4 | 6 | 15 | 15 | 40 |  |
| Erection |  |  |  |  |  |  |
| Plant Energization and | 5 | 10 | 15 | 0 | 30 |  |
| Commissioning |  |  |  |  |  |  |
| Construction Punchlist | 1 | 1 | 3 | 10 | 15 |  |
| Clean-Up |  |  |  |  |  |  |
| TOTALS | 31 | 44 | 102 | 76 | 253 |  |