Construction Scheduling

- Work Breakdown Structure (WBS) Milestones

| Activity ID | Activity Description |  |  |
| --- | --- | --- | --- |
| M100 | Advertise Date (Start Milestone) |  |  |
| M200 | Bid Date (Start Milestone) |  |  |
| M300 | Award Date (Start Milestone) |  |  |
| M400 | Start Design Work (Design/Build only) (Start Milestone) |  |  |
| M480 | Complete Design Work (Design/Build only) (Finish Milestone) |  |  |
| M500 | Construction Start Date (Start Milestone) |  |  |
| M600 | Stage_ Complete (increase by 5) (Finish Milestone) |  |  |
| M700 | Interim Completion Date(s) (Increase by 10) (Finish Milestone) |  |  |
| M800 | ROW Availability Date(s) (Increase by 5) (Finish Milestone) |  |  |
| M900 | Substantial Completion (Finish Milestone) |  |  |
| M950 | Completion (Finish Milestone) |  |  |
| 4.1.1 Work Breakdown Structure |  |  |  |
| WBS Code |  | Title |  |
| 0 |  | Milestones |  |
| C |  | Construction |  |
| C.00 |  | Administrative |  |
| C.01 |  | Stage 1 |  |
| C.01.1A |  | Stage 1 A |  |
| C.01.1B |  | Stage 1 B |  |
| C.01.1C |  | Stage 1 C |  |
| C.01.1D |  | Stage 1 D |  |
| C.01.1E |  | Stage 1 E |  |
| C.02 |  | Stage 2 |  |
| C.02.2A |  | Stage 2 A |  |
| C.02.2B |  | Stage 2 B |  |
| C.02.2C |  | Stage 2 C |  |
| C.02.2D |  | Stage 2 D |  |
| C.02.2E |  | Stage 2 E |  |
| C.03 |  | Stage 3 |  |
| C.03.3A |  | Stage 3 A |  |
| C.03.3B |  | Stage 3 B |  |
| C.03.3C |  | Stage 3 C |  |
| C.03.3D |  | Stage 3 D |  |
| C.03.3E |  | Stage 3 E |  |
| C.10 |  | Final Cleanup |  |
| D |  | Design (Design/Build only) |  |
| P |  | Procurement |  |
| P.CS |  | Contractor Submittals (Not Materials) |  |
| P.CS.01 |  | Safety Plan |  |
| P.CS.02 |  | Night Lighting |  |
| P.CS.03 |  | Demolition |  |
| P.CS.04 |  | Disposal |  |
| P.CS.05 |  | Paving |  |
| P.CS.06 |  | Steel Erection |  |
| P.CS.07 |  | Health and Safety Plan |  |
| P.CS.08 |  | Deck Placement |  |

| P.PP | Permits |  |
| --- | --- | --- |
| P.PP.01 | Environmental |  |
| P.PP.02 | Dewatering |  |
| P.MS | Material Submittals (Long Lead Items) |  |
| P.MS .01 | Concrete |  |
| P.MS .02 | Structural Steel |  |
| P.MS .03 | Asphalt |  |
| P.MS .04 | Electrical |  |
| P.MS .05 | Sheeting/Cofferdam |  |
| P.WD | Working Drawings |  |
| P.WD .01 | Bridge Working Drawings |  |
| P.WD.01.01 | Bridge Working Drawings Requiring Design |  |
| P.WD.01.01.01 | Structural Steel Working Drawings |  |
| P.WD.01.01.02 | Structural Bearings |  |
| P.WD.01.01.03 | Prestressed Concrete Beams |  |
| P.WD.01.01.04 | Prestressed Concrete Piles |  |
| P.WD.01.01.05 | Expansion Dams |  |
| P.WD.01.01.06 | Cofferdams |  |
| P.WD.01.01.07 | Sheeting |  |
| P.WD.01.01.08 | Machinery for Movable Bridges |  |
| P.WD.01.01.09 | Electrical Items for Movable Bridges |  |
| P.WD.01.01.10 | Precast Concrete Culverts |  |
| P.WD.01.01.11 | Steel Bridge Deck Forms |  |
| P.WD.01.01.12 | Prefabricated Modular Walls |  |
| P.WD.01.01.13 | Mechanical Stabilized Earth (MSE) Walls |  |
| P.WD.01.01.14 | Concrete Crib Walls |  |
| P.WD.01.01.15 | Alternate Retaining Wall Design |  |
| P.WD.01.01.16 | Temporary Structures |  |
| P.WD.01.01.17 | Temporary Shielding |  |
| P.WD.01.01.18 | Electrical Items not pre-approved |  |
| P.WD.01.02 | Bridge Working Drawings Not Requiring Design |  |
| P.WD.01.02.01 | Structural Steel Working Drawings |  |
| P.WD.01.02.02 | Structural Bearings |  |
| P.WD.01.02.03 | Prestressed Concrete Beams |  |
| P.WD.01.02.04 | Prestressed Concrete Piles |  |
| P.WD.01.02.05 | Expansion Dams |  |
| P.WD.01.02.06 | Cofferdams |  |
| P.WD.01.02.07 | Machinery for Movable Bridges |  |
| P.WD.01.02.08 | Electrical Items for Movable Bridges |  |
| P.WD.01.02.09 | Strip Seals |  |
| P.WD.01.02.10 | Armored Deck Joints |  |
| P.WD.01.02.11 | Bridge Storm Drains |  |
| P.WD.01.02.12 | Sign Support Structures |  |
| P.WD.01.02.13 | GA Sign Support Posts |  |
| P.WD.01.02.14 | Noise Barriers |  |
| P.WD.01.02.15 | Bridge Railings and Fencing Anchorages |  |
| P.WD.01.02.16 | Sign Legends |  |
| P.WD.02 | Road Working Drawings |  |
| P.WD.02.01 | Road requiring design |  |
| P.WD.02.01.01 | Impact attenuators |  |
| P.WD.02.01.02 | Sheeting |  |
| Construction Scheduling Manual, 2013 |  | Pa |

| P.WD.02.01.03 | Electrical items not pre-approved |
| --- | --- |
| P.WD.02.02 | Road not requiring design |
| P.WD.02.02.01 | Impact attenuators |
| P.WD.02.02.02 | Sign legends |
| P.WD.02.02.03 | Recycled/synthetic routed spacers |
| U | Utility |

4.2	Standard Activity Codes

4.2.1 RESP Responsibility

| RESP Code | Title |  |  |
| --- | --- | --- | --- |
| CONP | Prime Contractor |  |  |
| CONA | Adjacent Contractor |  |  |
| NACO | Army Corp of Engineers |  |  |
| NCOG | Coast Guard |  |  |
| NDBC | Delaware Bridge Commission |  |  |
| NDEP | New Jersey DEP |  |  |
| NDOT | New Jersey Department of Transportation |  |  |
| NDPA | Delaware Port Authority |  |  |
| NSJT | South Jersey Transportation Authority |  |  |
| NGSP | NJ Highway Authority |  |  |
| NPCM | Pinelands Commission |  |  |
| NPPA | Palisades Parkway |  |  |
| NPTA | Port Authority of NY and NJ |  |  |
| NTPK | New Jersey Turnpike |  |  |
| THRD | Third Party (Property owners, etc.) |  |  |
| UACE | Atlantic City Electric DBA Connective |  |  |
| UAMT | Amtrak |  |  |
| UATT | AT&T |  |  |
| UCBL | Cable Utility |  |  |
| UCVE | City of Vineland Electric Co. |  |  |
| UELG | Elizabethtown Gas |  |  |
| UELW | Elizabethtown Water Company |  |  |
| UGPN | JCP&L DBA GPU Energy - (North) |  |  |
| UGPS | JCP&L DBA GPU Energy - (South) |  |  |
| UMCI | MCI WorldCom |  |  |
| UMIW | Middlesex Water |  |  |
| UNGN | New Jersey Natural Gas (North) |  |  |
| UNGS | New Jersey Natural Gas (South) |  |  |
| UNJT | New Jersey Transit |  |  |
| UNJW | New Jersey American Water |  |  |
| UNWC | United Water Company |  |  |
| UPEC | Public Service Electric (Central) |  |  |
| UPEM | Public Service Electric (Metropolitan) |  |  |
| UPEP | Public Service Electric (Palisades) |  |  |
| UPES | Public Service Electric (Southern) |  |  |
| UPGN | Public Service Gas (North) |  |  |
| UPGS | Public Service Gas (South) |  |  |
| UPVS | Passaic Valley Sewerage Commission |  |  |
| UPVW | Passaic Valley Water Commission |  |  |
| UREL | Rockland Electric |  |  |
| URCR | Consolidated Rail Corporation |  |  |
| URNS | Norfolk and Southern Railroad |  |  |
| URCS | CSX Transportation Inc. |  |  |
| URNY | New York Susquehanna & Western Railway Corporation |  |  |
| USCC | Sprint Communications Company L.P. |  |  |
| USJG | South Jersey Gas |  |  |
| USPT | Sprint DBA United Telephone Co of NJ |  |  |
| Construction Scheduling Manual, 2013 |  | Page 7 |  |

| 1316 | Freehold Borough |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1317 | Freehold Township |  |  |  |  |  |  |  |  |  |
| Construction Scheduling Manual, 2013 |  |  |  |  |  | Page 14 |  |  |  |  |
| ITEM |  | Type 1 |  | Type 2 | Type 3 |  | Type 4 | Type 5 |  |  |
|  |  | Construction |  | Reconstruction | Widening |  | Resurfacing | Intersections |  |  |
| Mobilization |  | 10 Days* |  | 10 Days* | 5 Days |  | 2 Days | 2 Days |  |  |
| Clearing Site |  | 4 Acres |  | 4 Acres | 4 Acres |  | N/A | N/A |  |  |
| Stripping |  | 2 Acres |  | 2 Acres | 1 Acres |  |  |  |  |  |
| Demolition of |  | 1 Unit |  | 1 Unit | 1 Unit |  | N/A | N/A |  |  |
| Buildings |  |  |  |  |  |  |  |  |  |  |
| Pest Control |  | 10 Days |  | 10 Days | 10 Days |  | N/A | N/A |  |  |
| Asbestos Clean-up |  |  |  |  |  |  |  |  |  |  |
| Resident and Small |  | 4 Days |  | 4 Days | 4 Days |  | N/A | N/A |  |  |
| Commercial |  |  |  |  |  |  |  |  |  |  |
| Large Commercial |  | 10 Days |  | 10 Days | 10 Days |  |  |  |  |  |
| Pavement Removal |  | N/A |  | 2250 SY | 2250 SY |  | 2500 SY | 300 | SY |  |
| Roadway Excavation |  | 3000 CY |  | 1000 CY | 1000 CY |  | N/A | N/A |  |  |
| Embankment |  | 1500 CY |  | 350 CY | 350 CY |  | N/A | N/A |  |  |
| Drainage Pipe |  |  |  |  |  |  |  |  |  |  |
| Includes 1 Structure |  |  |  |  |  |  |  |  |  |  |
| 36 inches and Smaller |  | 300 | LF | 150 LF | 150 LF |  | N/A | 150 | LF |  |
| Larger than 36 inches |  |  |  |  |  |  |  |  |  |  |
|  |  | 100 | LF | 60 LF | 60 LF |  | N/A | 60 LF |  |  |
| Reset Castings |  | N/A |  | 5 Units | 5 Units |  | 5 Units | 5 Units |  |  |
| Extension Frames, |  | N/A |  | 12 Units | 12 Units |  | 12 Units | 12 Units |  |  |
| Rings and Grates |  |  |  |  |  |  |  |  |  |  |
| Subbase |  | 350 | CY | 250 CY | 150 CY |  | N/A | 50 CY |  |  |
| Aggregate Base |  | 350 | CY | 250 CY | 150 CY |  | N/A | 50 CY |  |  |
| Course |  |  |  |  |  |  |  |  |  |  |
| HMA |  | 1500 TONS |  | 1000 TONS | 750 |  | 1300 TONS | 250 | TONS |  |
|  |  |  |  |  | TONS |  |  |  |  |  |
| Concrete |  | 2500 SY |  | 1000 SY | 750 SY |  | N/A | 225 | SY |  |
| Base or Surface |  |  |  |  |  |  |  |  |  |  |
| Course |  |  |  |  |  |  |  |  |  |  |

able A (Con’t) - Production Rates For Roadway Items

| ITEM | Type 1 |  | Type 2 |  | Type 3 |  | Type 4 |  | Type 5 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Construction |  | Reconstruction |  | Widening |  | Resurfacing |  | Intersections |  |
| Concrete Bridge | 200 | SY | 200 | SY | 200 | SY | N/A |  | N/A |  |
| Approach |  |  |  |  |  |  |  |  |  |  |
| Milling (up to 2 | N/A |  | 6000 SY |  | 6000 SY |  | 6000 SY |  | 2500 SY |  |
| inches thick) |  |  |  |  |  |  |  |  |  |  |
| Concrete Barrier | 400 | LF | 350 | LF | 350 | LF | 250 | LF | N/A |  |
| Curb |  |  |  |  |  |  |  |  |  |  |
| Concrete Vertical | 500 | LF | 400 | LF | 400 | LF | 300 | LF | 200 | LF |
| Curb |  |  |  |  |  |  |  |  |  |  |
| Concrete Sidewalk | 225 | SY | 200 | SY | 200 | SY | 150 | SY | 150 | SY |
| Electrical Conduit | 600 | LF | 400 | LF | 400 | LF | 150 | LF | 150 | LF |
| Fiber Optic Conduit | 1000 LF |  | 1000 LF |  | 1000 LF |  | 1000 LF |  | N/A |  |
| Electrical Wire | 1200 LF |  | 1200 LF |  | 1200 LF |  | 300 | LF | 300 | LF |
| Lighting Standards | 4 Unit |  | 4 Unit |  | 4 Unit |  | N/A |  | 4 Unit |  |
| Traffic Signal | 20 Days per |  | 20 Days per |  | 20 Days per |  | 20 Days per |  | 20 Days per |  |
| Installation (1) | Intersection |  | Intersection |  | Intersection |  | Intersection |  | Intersection |  |
| Reset Beam Guide | N/A |  | 500 | LF | 500 | LF | 400 | LF | N/A |  |
| Rail |  |  |  |  |  |  |  |  |  |  |
| Beam Guide Rail | 750 | LF | 750 | LF | 750 | LF | 500 | LF | N/A |  |
| Chain Link Fence | 400 | LF | 400 | LF | 400 | LF | N/A |  | N/A |  |
| Overhead Sign | 15 Days per |  | 15 Days per |  | 15 Days per |  | 15 Days per |  | N/A |  |
| Structure (2) | Structure |  | Structure |  | Structure |  | Structure |  |  |  |
| Landscaping, Turf | 10,000 SY |  | 10,000 SY |  | 10,000 SY |  | N/A |  | N/A |  |
| Landscape, Planting | Planting |  | Planting |  | Planting |  | Planting |  | N/A |  |
| (3) | Season |  | Season |  | Season |  | Season |  |  |  |
| Final Acceptance (4) | 60 Calendar |  | 60 Calendar |  | 60 Calendar |  | 60 Calendar |  | 60 Calendar |  |
|  | Days |  | Days |  | Days |  | Days |  | Days |  |

Note: Production Rates are based on 8-hour working day per crew. (1) Manufacturing and delivery of steel traffic signal poles requires 4 months,

aluminum lighting and traffic signal poles require 2 months and traffic signal controllers require 4 months.

- Allow 2 months for working drawing approval, fabrication and delivery.

- Optimal Planting seasons - from March 1 to May 15 and from August 15 to December 1.

- These are minimum time frames.

Construction Scheduling Manual, 2013	Page 26

- Table B

Production Rates For Bridge Items

|  |  | Type 1 | Type 2 | Type 3 | Type 4 | Type 5 |
| --- | --- | --- | --- | --- | --- | --- |
|  | ITEM | Construction | Reconstruction | Superstruc | Deck | Overlay |
|  |  |  |  | ture |  |  |
|  | Cofferdams | 20 days | 20 days | N/A | N/A | N/A |
|  | Retaining Walls (1,3) | 20 days / | 20 days/ | N/A | N/A | N/A |
|  | (Cast-in-Place) | 100 LF | 100 LF |  |  |  |
|  | Retaining Walls (MSE | 15 days / 100 | 15 days / 100 LF | MA | NA | NA |
|  | etc) | LF |  |  |  |  |
|  | Box Culverts | 10 days / 30 LF | 10 days / 30 LF | N/A | N/A | N/A |
|  | (Cast-in-Place) |  |  |  |  |  |
|  | Box Culverts (2) | 5 days / 30 LF | 5 days / 30 LF | N/A | N/A | N/A |
|  | (Precast) |  |  |  |  |  |

Notes:

Production Rates are based on 8-hour working day per crew. For two bridges add 50%, for each additional bridge add 25%.

For Stage Construction, consider each stage to be a separate bridge.

For bridges over water or railroads add 30 days, except for Type 5 for which no adjustment is necessary.

Production rates include the time required for concrete curing.

- Add 5 days per 100 LF if temporary sheeting is required.

- Includes excavation and placing, allow 3-4 months for working drawing approval, fabrication and delivery.

- Use for Reinforced Earth, Double Wall and Anchored Walls.

Type 1 = New Construction on new alignment.

Type 2 = Remove existing bridge and construct new bridge at same location. Type 3 = Replace deck and beams including minor substructure repair.

Type 4 = Replace deck.

Type 5 = Deck patching and LMC overlay (subtract 10 days if overlay is bituminous concrete).

Construction Scheduling Manual, 2013	Page 27

- Table C

Bridge Item Production Rates on a One Span Bridge (40 to 100 feet Range)

|  |  | Bridge |  |  |  | Type 1 |  | 2 |  |  |  | 3 |  | 4 |  |  |  | 5 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Type/Bridge |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Item |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | New on |  | New on |  |  |  | Superstructure |  | Deck |  |  |  | B, C |  |  |
|  |  |  |  |  |  | New |  | Same |  |  |  | Replacement |  | Replacement |  |  |  | & LMC |  |  |
|  |  |  |  |  |  | Alignment |  | Alignment |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Demolition | -- |  |  |  |  | 16-28 days |  |  |  | 8-16 days |  | 7-14 days | -- |  |  |  |  |  |
|  |  | Foundation |  |  |  | 2-4 days |  | 2-4 days | -- |  |  |  | -- |  | -- |  |  |  |  |  |
|  |  | Excavation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Piles |  |  |  | 4-6 days |  | 4-6 days | -- |  |  |  | -- |  | -- |  |  |  |  |  |
|  |  | Footing |  |  |  | 2-4 days |  | 2-4 days | -- |  |  |  | -- |  | -- |  |  |  |  |  |
|  |  | Abutment, Pier, & |  |  |  | 6-8 days |  | 6-8 days | -- |  |  |  | -- |  | -- |  |  |  |  |  |
|  |  | WW’s |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Substructure |  |  |  | 14 days |  | 14 days | -- |  |  |  | -- |  | -- |  |  |  |  |  |
|  |  | Curing |  |  |  | 2-4 days |  | 2-4 days |  |  |  | 2-4 days | -- |  | -- |  |  |  |  |  |
|  |  | Framing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Deck Joints |  |  |  | 2-4 days |  | 2-4 days |  |  |  | 2-4 days |  | 2-4 days |  |  |  | 2-4 days |  |  |
|  |  | Deck Forms |  |  |  | 7-12 days |  | 7-12 days |  |  |  | 7-12 days |  | 7-12 days | -- |  |  |  |  |  |
|  |  | Shear Connectors |  |  |  | 1-2 days |  | 1-2 days |  |  |  | 1-2 days |  | 1-2 days | -- |  |  |  |  |  |
|  |  | Deck |  |  |  | 2-4 days |  | 2-4 days |  |  |  | 2-4 days |  | 2-4 days | -- |  |  |  |  |  |
|  |  | Deck Slab Curing |  |  |  | 14 days |  | 14 days |  |  |  | 14 days |  | 14 days | -- |  |  |  |  |  |
|  |  | Header |  |  |  | 1-2 days |  | 1-2 days |  |  |  | 1-2 days |  | 1-2 days | -- |  |  |  |  |  |
|  |  | Parapets |  |  |  | 2 days |  | 2 days |  |  |  | 2 days |  | 2 days | -- |  |  |  |  |  |
|  |  | Preformed Joint |  |  |  | 1 day |  | 1 day |  |  |  | 1 day |  | 1 day |  |  |  | 1 day |  |  |
|  |  | Railing/Fence |  |  |  | 3 days |  | 3 days |  |  |  | 3 days |  | 3 days | -- |  |  |  |  |  |
|  |  | Sawcut Deck |  |  |  | 1 day |  | 1 day |  |  |  | 1 day |  | 1 day |  |  |  | 1 day |  |  |
|  |  | Substructure | -- |  |  |  | -- |  |  |  |  | 6-12 days |  | 2-4 days | -- |  |  |  |  |  |
|  |  | Rehabilitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Deck Repairs | -- |  |  |  | -- |  | -- |  |  |  | -- |  | 6-12 |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | days |  |  |
|  |  | Total |  |  |  | 64-85 days |  | 80-113 days |  |  |  | 50-77 days |  | 43-63 days | 26-36 |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | days |  |  |

Allow 2 months (steel beams) and 3 months (concrete beams) for working drawing approval, fabrication and delivery. Designer will verify anticipated timeframes prior to Final Submission.

Construction Scheduling Manual, 2013	Page 28

- Table D

Bridge Item Production Rates on a Two Span Bridge (180 to 200 feet Range)

|  | Bridge |  |  | Type 1 |  |  | 2 |  |  | 3 |  |  | 4 |  | 5 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Type/Bridge |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Item |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | New on |  |  | New on |  |  | Superstructure |  |  | Deck |  | B, C & |  |
|  |  |  |  | New |  |  | Same |  |  | Replacement |  |  | replacement |  | LMC |  |
|  |  |  |  | Alignment |  |  | Alignment |  |  |  |  |  |  |  |  |  |
|  | Demolition |  | -- |  |  |  | 26-48 days |  |  | 16-32 days |  |  | 14-28 days |  | -- |  |
|  | Foundation |  |  | 3-5 days |  |  | 3-5 days |  | -- |  |  | -- |  |  | -- |  |
|  | Excavation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Piles |  |  | 6-10 days |  |  | 6-10 days |  | -- |  |  | -- |  |  | -- |  |
|  | Footing |  |  | 4-8 days |  |  | 4-8 days |  | -- |  |  | -- |  |  | -- |  |
|  | Abutment, Pier, & |  |  | 9-13 days |  |  | 9-13 days |  | -- |  |  | -- |  |  | -- |  |
|  | WW’s |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Substructure |  |  | 14 days |  |  | 14 days |  | -- |  |  | -- |  |  | -- |  |
|  | Curing |  |  | 4-8 days |  |  | 4-8 days |  |  | 4-8 days |  | -- |  |  | -- |  |
|  | Framing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deck Joints |  |  | 3-6 days |  |  | 3-6 days |  |  | 3-6 days |  |  | 3-6 days |  | 3-6 days |  |
|  | Deck Forms |  |  | 14-24 days |  |  | 14-24 days |  |  | 14-24 days |  |  | 14-24 days |  | -- |  |
|  | Shear Connectors |  |  | 2-4 days |  |  | 2-4 days |  |  | 2-4 days |  |  | 2-4 days |  | -- |  |
|  | Deck |  |  | 4-8 days |  |  | 4-8 days |  |  | 4-8 days |  |  | 4-8 days |  | -- |  |
|  | Deck Slab Curing |  |  | 14 days |  |  | 14 days |  |  | 14 days |  |  | 14 days |  | -- |  |
|  | Header |  |  | 1-2 days |  |  | 1-2 days |  |  | 1-2 days |  |  | 1-2 days |  | -- |  |
|  | Preformed Joint |  |  | 2 days |  |  | 2 days |  |  | 2 days |  |  | 2 days |  | 2 days |  |
|  | Parapets |  |  | 4 days |  |  | 4 days |  |  | 4 days |  |  | 4 days |  | -- |  |
|  | Railing/Fence |  |  | 6 days |  |  | 6 days |  |  | 6 days |  |  | 6 days |  | -- |  |
|  | Sawcut Deck |  |  | 1-2 days |  |  | 1-2 days |  |  | 1-2 days |  |  | 1-2 days |  | 1-2 days |  |
|  | Substructure |  | -- |  |  | -- |  |  |  | 9-18 days |  |  | 3-6 days |  | -- |  |
|  | Rehabilitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deck Repairs |  | -- |  |  | -- |  |  | -- |  |  | -- |  |  | 12-24 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | days |  |
|  | Working Drawing |  | 45 |  |  | 45 |  |  | 45 |  |  | 45 |  |  | 45 |  |
|  | Approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | TOTAL |  |  | 91-130 days |  | 117-178 |  |  |  | 80-130 days |  |  | 68-106 days |  | 36-56 |  |
|  |  |  |  |  |  |  | days |  |  |  |  |  |  |  | days |  |

Construction Scheduling Manual, 2013	Page 36

Appendix D

Sample 1 Time Impact Evaluation (TIE) - Form DC-186

Construction Scheduling Manual, 2013	Page 37

Sample 2 Time Impact Evaluation (TIE) - Form DC-186

Construction Scheduling Manual, 2013	Page 38

Construction Scheduling Manual, 2013	Page 39

Construction Scheduling Manual, 2013	Page 40

Construction Scheduling Manual, 2013	Page 41

Construction Scheduling Manual, 2013	Page 42