# Construction Schedule Template

|  | ID; Outline Number; Name; Duration; Predecessors; Start; Finish. 1; 1; Contracts. 2; 1.1; - Supply Lot Sale Agreement. 3; 1.2; - Supply Construction Agreement. 4; 1.3; - Supply Contract Plans. 5; 1.4; - Supply Contract Specifications. 6; 1.5; - Supply Contract Site Plan. 7; 1.6; - Secure Financing. 8; 1.7; - Construction Loan Settlement. 9; 2; Document Review & Revision. 10; 2.1; - Review & Finalize Plans. 11; 2.2; - Review & Finalize Specifications. 12; 2.3; - Review & Finalize Site Plan. 13; 2.4; - Print Construction Drawings. 14; 2.5; - Approve Revised Plans. 15; 2.6; - Approve Revised Specifications. 16; 2.7; - Approve Revised Site Plan. 17; 3; Bids & Contracts. 18; 3.1; - Make Copies of Plans. 19; 3.2; - Make Copies of Specifications. 20; 3.3; - Distribute Plans & Specifications. 21; 3.4; - Receive Bids. 22; 3.5; Review Bids. 25; 3.6; - Execute Subcontractor Agreements. 26; 4; Grading & Building Permits. 27; 4.1; - Schedule lot stake-out. 28; 4.2; - Stake lot. 29; 4.3; - File Grading Permit Application. 30; 4.4; - File Building Permit Application. 31; 4.5; - Post Lot Identification. 32; 4.6; - Meet Sed. Control Insp.. 33; 4.7; - Walk Lot w/ Owner. 34; 4.8; - Install Construction Entrance. 35; 4.9; - Install Sediment Controls. 36; 4.10; - Sediment Control Insp.. 37; 4.11; - Grading Permit Issued. 38; 4.12; - County Permit Process. 39; 4.13; - Building Permit Approved. 40; 4.14; - Pay Permit Fees and Excise Taxes. 41; 4.15; - Building Permit Issued. 42; 5; Site Work. 43; 5.1; - Clear Lot. 44; 5.2; - Strip Topsoil & Stockpile. 45; 5.3; - Stake Lot for Excavation. 46; 5.4; - Rough grade lot. 47; 5.5; - Excavate for foundation. 48; 6; Foundation. 49; 6.1; - Layout footings. 50; 6.2; - Dig Footings & Install Reinforcing. 51; 6.3; - Footing Inspection. 52; 6.4; - Pour footings. 53; 6.5; - Pin Footings. 54; 6.6; - Stock Block, Mortar, Sand. 55; 6.7; - Build Block Foundation. 56; 6.8; - Foundation Certification. 57; 6.9; - Draw #1 (Location Survey). 58; 6.10; - Fill Block Cores w/ Concrete. 59; 6.11; - Steel Delivery. 60; 6.12; - Set Lintels, Bolts, Cap Block. 61; 6.13; - Lumber Delivery. 62; 6.14; - Waterproofing and Drain Tile. 63; 7; Rough Carpentry. 64; 7.1; - Set Steel. 65; 7.2; - 1st Floor Deck Framing. 66; 7.3; - 1st Floor Wall Framing. 67; 7.4; - Draw #2 (First Floor Deck). 68; 7.5; - 2nd Floor Deck Framing. 69; 7.6; - Draw #3 (Second Floor Deck). 70; 7.7; - 2nd Floor Wall Framing. 71; 7.8; - Set Roof Trusses. 72; 7.9; - Frame Roof. 73; 7.10; - Install Roof Plywood. 74; 7.11; - Install Windows & Doors. 75; 7.12; - Frame Basement. 76; 7.13; - Frame Basement Bulkheads. 77; 8; Concrete Slabs. 78; 8.1; - Basement Slab Preparation. 79; 8.2; - Termite Treatment Basment Slab. 80; 8.3; - Slab Inspection. 81; 8.4; - Pour Basement Slab. 82; 8.5; - Prep Garage Slab. 83; 8.6; - Termite Treatment Garage Slab. 84; 8.7; - Pour Garage Slab. 85; 9; H.V.A.C.. 86; 9.1; - HVAC Layout & Measure. 87; 9.2; - HVAC Rough-in. 88; 9.3; - HVAC Set Indoor Units. 89; 9.4; - HVAC Temporary Heat. 90; 10; Plumbing Rough-in. 91; 10.1; - Plumbing Sub-slab. 92; 10.2; - Plumbing Layout. 93; 10.3; - Plumbing rough-in. 94; 11; County Plumbing Sub-slab Inspection. 95; 12; County Plumbing Rough-in Inspection. 96; 13; Electric Rough-in. 97; 13.1; - Set Electric Boxes; 2.00d; 74; Fri 10/24/14; Mon 10/27/14. 98; 13.2; - Install Electric Service Panel. 99; 13.3; - Electrical Walk-through. 100; 13.4; - Electrical Rough-wire. 101; 14; Specialty Rough-ins. 102; 14.1; - Central Vacuum Rough-in. 103; 14.2; - Alarm System Rough-in. 104; 14.3; - Telephone System Rough-in. 105; 14.4; - Television System Rough-in. 106; 14.5; - Audio Visual Rough-in. 107; 15; County Electrical inspection. 108; 16; Draw #5 (Rough-ins complete). 109; 17; County Framing Inspection. 110; 18; Roofing. 111; 18.1; - Roofing Paper Installed. 112; 18.2; - Draw #4 (Roof, windows, doors). 113; 18.3; - Stock Roof Shingles. 114; 18.4; - Install Roof Shingles. 115; 19; Exterior Finishes. 116; 19.1; - Siding. 117; 19.2; - Exterior Trim. 118; 19.3; - Brick Arch Forms. 119; 19.4; - Brick Veneer. 120; 20; Insulation. 121; 20.1; - Caulk & Air Seal. 122; 20.2; - Draft & Fire Stop. 123; 20.3; - Batt Insulation. 124; 21; County Insulation Inspection. 125; 22; BGE Energy Wise Inspection. 126; 23; Drywall. 127; 23.1; - Stock Drywall. 128; 23.2; - Hang Drywall. 129; 23.3; - Remove Scrap Drywall. 130; 23.4; - Tape and Finish Drywall. 131; 23.5; - Sand Drywall. 132; 23.6; - Drywall Point-up. 133; 24; Draw #6 (Insulation & drywall applied). 134; 25; Floor Finishes. 135; 25.1; - Ceramic Tile. 136; 25.2; - Install Hardwood Floor. 137; 25.3; - Sand, Stain, Seal Hardwood. 138; 25.4; - Install Carpet. 139; 25.5; - Final Coat Hardwood. 140; 26; Paint. 141; 26.1; - Prep Drywall for Prime Coat. 142; 26.2; - Prime Paint Drywall. 143; 26.3; - Prep Trim for Prime Coat. 144; 26.4; - Prime Trim. 145; 26.5; - Finish Coat Trim. 146; 26.6; - Finish Coat Drywall. 147; 26.7; - Caulk Exterior Windows & Doors. 148; 26.8; - Finish Coat Exterior Trim & Siding. 149; 27; Draw #7 (Roofing, masonry, siding). 150; 28; Interior Trim. 151; 28.1; - Interior Trim Delivery. 152; 28.2; - Install Interior Doors. 153; 28.3; - Install Interior Trim. 154; 28.4; - Install Cabinetry. 155; 28.5; - Install Appliances. 156; 28.6; - 1st Punch-out Interior Trim. 157; 29; H.V.A.C. Trim. 158; 29.1; - Install Grills & Registers for Paint. 159; 29.2; - Set Outdoor Units. 160; 30; Plumbing Trim. 161; 30.1; - Set Fixtures. 162; 30.2; - Connect Appliances. 163; 31; County Final Plumbing Inspection. 164; 32; Exterior Landscaping. 165; 32.1; - Rough Final Grade. 166; 32.2; - Patios. 167; 32.3; - Porches. 168; 32.4; - Sidewalks. 169; 32.5; - Decks. 170; 32.6; - Driveways. 171; 32.7; - Final Grade and Seed. 172; 33; Electrical Final Trim. 173; 33.1; - Switch & Plug. 174; 33.2; - Install Fixtures. 175; 33.3; - Connect Appliances. 176; 34; Hardware. 177; 34.1; - Door Hardware. 178; 34.2; - Bath Hardware. 179; 34.3; - Mirrors. 180; 34.4; - Shower Doors. 181; 35; Draw #8 (Prime paint, cabinets, doors). 182; 36; Draw #9 (Trim, furnace, hrdwd, tile, rails). 183; 37; Draw #10 (Plumbing & elec. trim, final paint). 184; 38; Final Building Inspection. 185; 39; Use & Occupancy Certificate. 186; 40; First Walk-thru. 187; 41; Draw #11 (Final payment per contract). 188; 42; Final Punch-out. 189; 42.1; - Punch Out Walk-thru List. 190; 42.2; - Trim and Adjust Doors. 191; 42.3; - Paint Touch-up. 192; 43; Cleaning. 193; 43.1; - Windows. 194; 43.2; - Rough Clean. 195; 43.3; - Final Clean. 196; 44; Final Walk-through. 197; 45; Move-in. |
| --- | --- |