CONSTRUCTION SCHEDULE TEMPLATE

| TASKS | START DATE | FINISH DATE |
| --- | --- | --- |
| - Surveyor staking foundation location (1/2 day) - Excavation and, if necessary, clearing and tree removal (1-2 days) - Footing and foundation work, including time for curing concrete, installing drain tile, waterproofing, back filling, etc. (2-3 weeks) - Framing (1-3 weeks) - Roofing and flashing work, chimney installation (1-2 weeks) - Window, exterior door installation, siding, trim (2-4 weeks) - Electrical, plumbing, other rough-ins. Note that this step overlaps with step 6 (1-2 weeks) - Walls and ceilings (2 weeks) - Finish work: interior trim, doors, floors, cabinets, painting, set fixtures, etc. (2-8 weeks) - Punch list, final inspection, etc. (1 week) |  |  |