This sample construction schedule can provide you with an idea of what to expect when building a modular home.

- Step 1: Land/Lot Development

- Purchase

- Clear Title (if not already owned)

- Accessible to Modular Transporter (conduct site accessibility study)

  - conduct prior to purchase if not already owned

- Perk / Probe Test (or public sewer if available)

  - conduct prior to purchase if not already owned

- Land Surveyed (if not already owned)

- Step 2: Forms/Procedures/Permits

- Select Modular Model, Options

- Develop and Finalize Prints, Plans, Options, Finishes and Specs

- Contracts Signed

- Sign-Off on Plans and Specs

- Secure Financing

- Set Target Occupancy Date

- Issue Deposit

- Establish Construction Activities/Schedule

- Obtain and Post Permits

  - Building

  - Electrical

  - Plumbing

  - Mechanical

  - Road/Culvert

- Application for Gas/Electrical Service

- Site Survey (stake out)

- Step 3: Foundation and Sitework

- Order Steel Beams and Columns

- Deliver Dumpster and Port-a-potty

- Site Preparation, Remove Obstacles

- Layout and Excavation

- Form Footings

- Pour Footings

- Footing Inspection

- Install Footing Drains and Basement Stone

- Install Under-Slab Utilities

- Block Delivery/Foundation Systems

- Construct/Install Foundation Walls

- Inspect Foundation Drains

- Apply Foundation Damp-Proofing and Vapor Barrier

- Install Anchor Clips/Bolts, Sill Plate and Sealer

- Install Sump Pump and Rough Plumbing

- Install Basement Windows

- Install Foundation Drain Tile and Cover

- Prep Opening in Floor for Posts/Support Columns

- Pour Basement Floor

- Backfill

- Step 4: Site Preparation

- Foundations and Footings are Completed

- Foundation is Square and Level

- Foundation and Footings have passed Inspection

- Obstacles for Crane and Transporters have been Removed

- Access Route for Crane and Transporters is planned

- Crane Pad is Ready and Firm

- Set Crew and Crane Schedules are Confirmed

- Bulldozer and Operator Scheduled and Confirmed

- Utility Crews have been Scheduled for Turn-off / Turn-on (if applicable)

- Weather Forecast for Set Day looks Adequate

Payment for Delivery Day Confirmed and Available

Step 5: Modular Home Set

- Modules Delivered/Received

- Unwrap Modules

- Check Inventory of Ship-Loose Materials

- Mark Mating Lines on the Foundation

- Locate Pick-Points on the Modules, Prepare for Lifting

- Module Set

- Fasten and Check Module

- Prepare Mating Surfaces

- Prepare Wires, Pipes, Ducts and Stairs

- Posts/Support Columns Set/Installed

- Stairs to Basement Set/Installed

- Lift Jointed Roof Sections with Crane

- Lift Dormers and Other Roof Elements

- Make the Home Weather-Tight and Secure

- Sign Set-Release

- Step 6: Exterior Finishing

- Siding Completed

- Masonry Work Completed

- Prime, Paint or Stain Exterior Surfaces

- Install Shutters

- Install Chimney Stack

- Install Gutters and Downspouts

- Optional Garages Completed

- Optional Porches, Decks and Patios Completed

- Step 7: Interior Electrical

- Install Circuit Breaker Box

- Install Meter Box, Conduit Master, Service Entrance Cable & Basement Cable

- Connect Wiring of Modular Units and Tie-In to Junction Box

- Connect Service in Garage and Outbuildings if Applicable

- Install Sump Pump

- Install 220v Service for Range/Dryer (or run gas line)

- Electrical Inspection

- Step 8: Plumbing Connections

- Drill/Install Well & Pump or Hook-Up to Public System

- Install/Inspect Septic and Drainage Systems of Hook-Up to Public Systems

- Install Shower Doors

- Install Supply and Drain Lines/Connect to Stubbing

- Install Gas Pipes to Range/Dryer/Water Heater if Applicable

- Check and Tighten Shut-Off Valves

- Plumbing Inspection

- Step 9: HVAC

- Install/Connect AC System

- Install Oil Tank and Line to Furnace if Applicable

- Install Electric Water Heater and Connect to Breaker Box

- Connect Chimney Flue Into Furnace

- For Baseboard Electrical Heat, Connect Circuits at Junction Box

- Vent Dryer

- Install Security System

- Connect Central Vac System

- Mechanical Inspection

- Step 10: Interior Finishing

- Finish/Patch Drywall

- Paint Interior Walls

- Finish Interior Trim and Doors/Adjust

- Install or Seam Vinyl, Hardwood, Laminate or Carpeting at Mate Walls

- Clean-Up

- Step 11: Exterior Final Finish

- Complete Garage Floors, Steps, Service Walks, etc.

- Install Exterior Lights and Bulbs

- Finish Grading

- Landscaping

- Garage Doors

- Exterior Clean-Up

- Step 12: Closing

- Punch List

- Final Clean-up - Remove Dumpsters & Port-a-potty

- Walk Through with Customer

- Final Building Inspection

- Occupancy Permit

- Owner Occupancy